## Sheet1
Risk ID | Risk Description | Risk Treatment | Date Due | Status | Risk Manager | Status Update
Risk 001 | There is a risk that an organised crime group is able to gain access to the Grant Application System resulting in a loss of confidentiality and integrity of personal data and company information | Enforce MFA on all accounts to prevent unauthorised access | 2023-07-31 | Amber | Jay Smith | MFA has been implemented on all administrator accounts Pilot roll out of MFA to all internal accounts started on 01/06
Risk 001 | There is a risk that an organised crime group is able to gain access to the Grant Application System resulting in a loss of confidentiality and integrity of personal data and company information | Create process for regular review of accounts and removal of redundant accounts | 2023-07-31 | Green | Jay Smith | New process is with IT leadership team for approval.
Risk 001 | There is a risk that an organised crime group is able to gain access to the Grant Application System resulting in a loss of confidentiality and integrity of personal data and company information | Enable monitoring on Grant Management Application and create process for monitoring of activities. | 2023-08-30 | Red | Jay Smith | Enabling the auditing function on the database caused significant degradation of the service. The database server has to be upgraded with additional memory.
Risk 002 | There is a risk that a cyber criminal is able to gain access to the backend database and amend company information, including bank details resulting in loss of integrity. | Enforce MFA on all database accounts to prevent unauthorised access | 2023-07-31 | Amber | Dee Rate | MFA has been implemented on all administrator accounts Pilot roll out of MFA to all internal accounts started on 01/06
Risk 002 | There is a risk that a cyber criminal is able to gain access to the backend database and amend company information, including bank details resulting in loss of integrity. | Enable encryption at rest on database. | 2023-08-31 | Green | Dee Rate | Encryption has been enabled on the pre-prod database. Extensive testing is ongoing, so far there has not been any negative impact on database performance.
Risk 003 | There is a risk that a privileged user is able to cover their track by removing footprints from an activity resulting in repudiation of an activity. | Establish and document process for security monitoring | 2023-07-31 | Red | Paula Singh | The database logging is not compartable with the current SIEM tooling. We are looking at alternative ways of implementing protective mmonitoring on the database.
Risk 004 | There is a risk that a malicious actor might upload a document containing malicious code resulting in compromise of the integrity of the Grant Management System. | Implement endpoint detection and response. | 2023-08-30 | Amber | Dee Rate | We are waiting for the infrastructure team to confirm if we have enough licenses. If not, additional licenses will have to be purchased. The purchasing process might result in additional delays in implementing this control.
Risk 005 | There is a risk that a cyber criminal might launch a denial of service attack against the grant application system resulting in the system being unavailable. | Arrange IT Health Check / Penetration Test. | 2023-10-30 | Green | Dee Rate | The penetration test will take place during the 1st week in September.
Risk 005 | There is a risk that a cyber criminal might launch a denial of service attack against the grant application system resulting in the system being unavailable. | Implement endpoint detection and response. | 2023-08-30 | Amber | Dee Rate | We are waiting for the infrastructure team to confirm if we have enough licenses. If not, additional licenses will have to be purchased. The purchasing process might result in additional delays in implementing this control.
Risk 006 | There is the risk that a cyber criminal might conduct a man-in-the-middle attack and gain access to sensitive information by sniffing the traffic between the end user workstation and the web application resulting in a disclosure of information or loss of confidentiality. | Encrypt network traffic | 2023-07-31 | Green | Paula Singh | Point to point encryption will be implemented before the security health check takes place.
Risk 007 | There is a risk that a hactivist or hacker may abuse weak database configuration and be able to perform admin task resulting in a compromise of the grant application system. | Implement CIS benchmarks | 2023-07-31 | Green | Paula Singh | CIS benchmarks are currently being tested in the pre-prod environment, there has not been any issues to date.
Risk 007 | There is a risk that a hactivist or hacker may abuse weak database configuration and be able to perform admin task resulting in a compromise of the grant application system. | Establish and document process for security monitoring | 2023-07-31 | Red | Paula Singh | The database logging is not compartable with the current SIEM tooling. We are looking at alternative ways of implementing protective mmonitoring on the database.
Risk 008 | There is a risk that a cloud service provider or supply chain staff gain access to change the system configuration or exfiltrate data resulting in a system compromise or data loss. | (1) Request a security management plan from supplier ALPHA. (2) Review the SMP for completeness and identify any weaknesses in the plan. (3) Obtain authorisation of the SMP. | 2023-08-30 | Red | Dee Rate | There are still a lot of issues to be resolved around the SMP with ALPHA.
Risk 010 | There is a risk that an employee with elevated privileges might make an accidental or unauthorised changed to the system resulting in a loss of integrity. | Enable Just-in-time privileged user management on the operating system and database | 2023-07-31 | Green | Paula Singh | Just-in-time privilege user management has been activated for a set of pilot users/administrators. On target to roll out to all administrators by 31/07/2023.
Risk 010 | There is a risk that an employee with elevated privileges might make an accidental or unauthorised changed to the system resulting in a loss of integrity. | Implement a configuration management system and regular configuration checks on operating systems and databases. | 2023-07-31 | Red | Paula Singh | A configuration management system is going through proof of concept (POC). We are behind schedule and will not meet the 31/07/2023 target date.
Risk 012 | There is a risk that cyber criminals are able to cover their track by removing footprints from an activity resulting in repudiation of an activity. | Establish and document process for security monitoring | 2023-07-31 | Red | Paula Singh | The database logging is not compartable with the current SIEM tooling. We are looking at alternative ways of implementing protective mmonitoring on the database.
Risk 013 | There is a risk that hostile state actors or cyber criminals might compromise a supplier's system by performing a supply chain attack, and use it gain unauthorised access to the grant management system resulting in loss of confidentiality and integrity. |  | 2023-07-31 | Green | Paula Singh | The suppliers will complete their SOC 2 certification before go-live. All security requirements will be included in the security management plan (SMP), and will be subject to monthly review with the supplier.
Risk 014 | There is a risk that a hardware failure or malfunction might lead to the grant application system being unavailable to grant users resulting in system compromise and loss of availability. | Create and obtain CTO approval for backup and restoration plan. The plan must include Recovery Time Objectives (RTO) and Recovery Point Objectives (RPO). | 2023-07-31 | Green | Paula Singh | The backup and restoration plans are being tested. Also waiting for sign-off by SLT.
Risk 014 | There is a risk that a hardware failure or malfunction might lead to the grant application system being unavailable to grant users resulting in system compromise and loss of availability. | Agree service level agreements for the service. | 2023-07-31 | Amber | Paula Singh | The SLA is being reviewed by SLT. Some major changes have been requested.