## Introduction
Threat likelihood | 5 - Almost certain / Frequent | Low 5 | Medium 10 | High 15 | High 20 | Very High 25
| 4 - Likely / Probable | Low 4 | Medium 8 | Medium 12 | High 16 | High 20
| 3 - Possible / Occasional | V. Low 3 | Low 6 | Medium 9 | Medium 12 | High 15
| 2 - Unlikely / Remote | V. Low 2 | Low 4 | Low 6 | Medium 8 | Medium 10
| 1 - Very Unlikely / Improbable | V. Low 1 | V. Low 2 | V. Low 3 | Low 4 | Low 5
Risk: Component of Threat likelihood and Impact |  | 1 - Minor | 2 - Marginal | 3 - Moderate | 4 - Severe | 5 - Critical
Impact
|  | V Low | Low | Medi | High | V High

## Impact Analysis
| Business Impact Levels - What is the most reasonable / realistic impact? TO BE UPDATED BY THE Organisation | [8 empty] | Business Impact Reference Table TO BE UPDATED BY THE CABINET OFFICE |  |  |  |  | Comments
| Compromise of Data Confidentiality (Accidental Disclosure / Leak / Theft) |  |  | Compromise of Integrity |  |  | Compromise of Availability (Disruption of services) |  |  | Minor | Marginal | Moderate | Severe | Critical
Financial | moderate | copy the moderate narative | put the score | marginal | copy the moderate narative | put the score | marginal | copy the moderate narative | put the score
Operational | [9 empty] | - Negligible/insignificant loss of management’s ability to effectively govern or operate the organisation | - Minor loss of management’s ability to effectively govern or operate the organisation (e.g. limited impairment in decision making) | - Moderate loss of management’s ability to effectively govern or operate the organisation (e.g. noticable impairment in decision making) | - Significant loss of management’s ability to effectively govern or operate the organisation (e.g. serious impairment in decision making) | - Substancial loss of management’s ability to effectively govern or operate the organisation (e.g. substancial impairment in decision making)
Legal and regulatory compliance
Reputational
Health and safety
FOTINI TO WORK on THIS

## Threat Analysis
Threat Profiling
|  | TS | LoL |  |  |  | Threat Events
Adversarial | Threat | Capability | Intent (history) & Motivation | Threat Level | Threat Rating | Threat Score | Ransomware | Phishing | DDoS | Credentials Stuffing
| Hostile State Actors | 5 | 3 | 15 | Substantial | 4
| Organised Crime | 4 | 5 | 20 | Severe | 5
| Direct action groups and Hacktivists | 3 | 4 | 12 | Substantial | 4
| Terrorist | 4 | 4 | 16 | Substantial | 4
| Cyber Criminals | 3 | 4 | 12 | Substantial | 4 |  | please check that the infor in here maps the Threat Assessment
| Employees (disgruntled, coerced) | 2 | 4 | 8 | Moderate | 3
| Investigative Journalists | 2 | 4 | 8 | Moderate | 3
| Individual Criminals | 2 | 4 | 8 | Moderate | 3
Accidental | Threat | Privilege | Competence & Culture | Threat Level | Threat level | Threat Score
| Business Users |  |  | 0 | Unrated | 0
| Privileged Users |  |  | 0 | Unrated | 0
| Customer |  |  | 0 | Unrated | 0
| Suppliers |  |  | 0 | Unrated | 0
Environmental | Threat | Severity | Predisposition & History | Threat Level | Threat Level | Threat Score
| Hardware malfunction or failure |  |  | 0 | Unrated | 4
| Damage to or loss of external communications |  |  | 0 | Unrated | 0
| Severe Weather Event |  |  | 0 | Unrated | 0
| Failure of environmental control systems |  |  | 0 | Unrated | 0
| Fire |  |  | 0 | Unrated | 0
| Flooding |  |  | 0 | Unrated | 0
| Organised crime | 4
| Hostile state actors | 5
| Investigative journalists | 4
| Action groups | 4
| Hactivist and hacking groups | 4
| Cyber criminals | 3
| Employee (disgruntled, coerced) | 3
| Employee (privileged) | 3
| Supplier/vendor/partner (external) | 3
| Business Users | 0 |  |  | Scale
| Privileged Users | 0 |  |  | severe | 5
| Customers | 0 |  |  | substantial | 4
| Suppliers | 0 |  |  | moderate | 3
| Hardware malfunction or failure | 4 |  |  | low | 2
| Damage to or loss of external communications | 0 |  |  | very low | 1
| Adverse Weather | 0
| Failure of environmental control systems | 0
| Fire | 0
| Flooding | 0

## Security Risk Tracker
Risk ID and Description |  | Risk Tracker | [11 empty] | Risk Assessment (Inherent Risk) | [7 empty] | Risk Management (Residual Risk)
Reference / Risk ID | Risk Description | Project Risk | Business Unit | Enterprise-level cyber risk | Accountable | Risk Owner | Residual Risk Rating | Updates/Progress | Date raised | Last updated | Escalate? | Information Asset | Component | Threat | Threat Event Type (STRIDE) | Threat Likelihood | Threat Likelihood Score | Impact | Impact Score | Inherent Risk Rating SCORE | Inherent Risk Rating | Target Risk Rating | Risk Treatment Approach | Mitigating Controls | Residual Likelihood | Threat Likelihood Score | Residual Impact | Impact Score | RR SCORE | Residual Risk Rating
Unique risk ID | A qualitative description of the risk.A qualitative description of the risk. Please articulate the risk in simple business language and include at a minimum who (organised criminals) could initiate a certain event (phishing) that compromises what assets/services because of what system weaknesses (vulnerabilities) and what could be the impact on business objectives. | The programme/project the risk is owned by | The Business Unit the risk is owned by. | The cyber risk category based on a pre-defined list of risk types. | Who is accountable for the risk? (SRO) | Who is responsible for managing the risk? | What is the residual risk rating? | Provide updates/comments on progress, including the date the update was provided. | Date risk was entered. | Date risk was last updated. | Should the risk be escalated to BU Risk Management? |  |  |  |  | The probability of the risk manifesting within the defined time frame. |  | What is the "realistic" impact of the risk should it manifest? |  |  | What is the inherent risk? | What level of risk is acceptable? | What approach are we taking to the risk? |  | What is the probability of the risk manifesting after treatment? |  | What is the "realistic" impact of the risk should it manifest? |  |  | What is the residual risk rating?
Risk 001 | There is a risk that an organised crime group is able to gain access to the Grant Application System resulting in a loss of confidentiality and integrity of personal data and company information | Grant Management Service | Department of Artificial Intelligence and Robotic Technologies |  | SRO | IAO | Medium | Risk was raised with SRO on 31/01/2023 and need to reduced to low | 31/01/2023 |  | Yes | Customer PII Customer Application Information | Grant Management Application (SaaS) | Organised Crime | Spoofing | 3 - Possible / Occasional | 3 | 4 - Severe | 4 | 12 | Medium | Low | Treat | 1. Implement MFA to mitigate the risk of unauthorised access - Principle 10 of NCSC Cloud Security Principles (Identity and authentication) 2. Secure user management, including removal of redundant accounts - Principle 9 of NCSC Cloud Security Principles (Secure user management) 3. Protective monitoring, including monitoring of suspicious activities e.g., fail access attempts, configuration change, etc. - Principle 5.2 of NCSC Cloud Security Principles (Protective monitoring) | 2 - Unlikely / Remote | 2 | 4 - Severe | 4 | 8 | Medium
Risk 002 | There is a risk that a cyber criminal is able to gain access to the backend database and amend company information, including bank details resulting in loss of integrity. | Grant Management Service | Department of Artificial Intelligence and Robotic Technologies |  | SRO | IAO | Low | Risk was raised with SRO on 31/01/2023 and risk will be accepted after successful treatment and reduction to Low. | 31/01/2023 |  | No | Customer PII Customer Application Information | Grant Management Application Database | Cyber Criminals | Spoofing | 3 - Possible / Occasional | 3 | 4 - Severe | 4 | 12 | Medium | Low | Treat | 1. Implement MFA to mitigate the risk of unauthorised access - Principle 10 of NCSC Cloud Security Principles (Identity and Authentication) 2. Secure user management, including removal of redundant accounts - Principle 9 of NCSC Cloud Security Principles (Secure user management) 3. Protective monitoring, including monitoring of suspicious activities e.g., fail access attempts, configuration change, etc. - Principle 5.2 of NCSC Cloud Security Principles (Protective monitoring) 4. Encrypt data at rest - Principle 2.3 of NCSC Cloud Security Principles (Data Encryption) | 2 - Unlikely / Remote | 2 | 3 - Moderate | 3 | 6 | Low
Risk 003 | There is a risk that a privileged user is able to cover their track by removing footprints from an activity resulting in repudiation of an activity. | Grant Management Service | Department of Artificial Intelligence and Robotic Technologies |  | SRO | IAO | Low | Risk was raised with SRO on 31/01/2023 and risk will be accepted after successful treatment and reduction to Low. | 2023-01-02 |  | No | Log Files | Backend Server | Employee (privileged) | Repudiation | 3 - Possible / Occasional | 3 | 3 - Moderate | 3 | 9 | Medium | Low | Treat | 1. Log protection Principle 2.3 of Cloud Security Principles (Data encryption) Principle 5.2 of Cloud Security Principles (Protective monitoring) 2. Security monitoring Principle 5.2 of Cloud Security Principles (Protective monitoring) | 2 - Unlikely / Remote | 2 | 3 - Moderate | 3 | 6 | Low
Risk 004 | There is a risk that a malicious actor might upload a document containing malicious code resulting in compromise of the integrity of the Grant Management System. | Grant Management Service | Department of Artificial Intelligence and Robotic Technologies |  | SRO | IAO | Medium | Risk was raised with SRO on 31/01/2023 and need to reduced to low | 2023-01-02 |  | Yes | Grant Management Application (SaaS) | Application Server | Cyber Criminals | Tampering | 4 - Likely / Probable | 4 | 3 - Moderate | 3 | 12 | Medium | Low | Treat | 1. Input validation - Principle 7 of Cloud Security Principles (Secure Development) 2. Malware protection - Principle 2.5 of Cloud Security Principles (Physical resilience and availability) 3. Web Application Firewall - Principle 2.5 of Cloud Security Principles (Physical resilience and availabilty) Principle 11 of Cloud Security Principles (External interface protection) | 3 - Possible / Occasional | 3 | 3 - Moderate | 3 | 9 | Medium
Risk 005 | There is a risk that a cyber criminal might launch a denial of service attack against the grant application system resulting in the system being unavailable. | Grant Management Service | Department of Artificial Intelligence and Robotic Technologies |  | SRO | IAO | Low | Risk was raised with SRO on 31/01/2023 and risk will be accepted after successful treatment and reduction to Low. | 31/01/2023 |  | No | Grant Management Application (SaaS) | Application Server | Cyber Criminals | Denial of Service | 3 - Possible / Occasional | 3 | 3 - Moderate | 3 | 9 | Medium | Low | Treat | 1. External penetration / ITHC test. 2. Load balancer / Web application firewall. 3. Malicious code is detected. - Principle 2.5 of NCSC Cloud Security Principles (Physical resilience and availabilty) Principle 5.2 of NCSC Cloud Security Principles (Protective monitoring) 4. Detected events are analysed to understand attack targets and methods. Principle 5.2 of NCSC Cloud Security Principles (Protective monitoring) | 2 - Unlikely / Remote | 2 | 2 - Marginal | 2 | 4 | Low
Risk 006 | There is the risk that a cyber criminal might conduct a man-in-the-middle attack and gain access to sensitive information by sniffing the traffic between the end user workstation and the web application resulting in a disclosure of information or loss of confidentiality. | Grant Management Service | Department of Artificial Intelligence and Robotic Technologies |  | SRO | IAO | Low | Risk was raised with SRO on 31/01/2023 and risk will be accepted after successful treatment and reduction to Low. | 2023-05-02 |  | No | Customer PII Customer Application Information | Public Network | Cyber Criminals | Information Disclosure | 2 - Unlikely / Remote | 2 | 3 - Moderate | 3 | 6 | Low | Low | Treat | 1. Encrypt network traffic Principle 1 of Cloud Security Principles (Data in transit protection) | 2 - Unlikely / Remote | 2 | 2 - Marginal | 2 | 4 | Low
Risk 007 | There is a risk that a hactivist or hacker may abuse weak database configuration and be able to perform admin task resulting in a compromise of the grant application system. | Grant Management Service | Department of Artificial Intelligence and Robotic Technologies |  | SRO | IAO | Low | Risk was raised with SRO on 31/01/2023 and risk will be accepted after successful treatment and reduction to Low. | 2023-01-02 |  | No | Grant Management Application Database | Backend Server | Hactivist and hacking groups | Escalation of Privilege | 3 - Possible / Occasional | 3 | 3 - Moderate | 3 | 9 | Medium | Low | Treat | 1. Secure configuration - Principle 5.4 of Cloud Security Principles (Configuration and change management) Principle 7 of Cloud Security Principles (Secure development) Principle 11 of Cloud Security Principles (External interface protection) 2. Security testing 3. Security monitoring Principle 5.2 of Cloud Security Principles (Protective. monitoring) | 2 - Unlikely / Remote | 2 | 3 - Moderate | 3 | 6 | Low
Risk 008 | There is a risk that a cloud service provider or supply chain staff gain access to change the system configuration or exfiltrate data resulting in a system compromise or data loss. | Grant Management Service | Department of Artificial Intelligence and Robotic Technologies |  | SRO | IAO | Medium | Risk was raised with SRO on 31/01/2023 and need to reduced to low | 31/01/2023 |  | Yes | Customer PII Customer Application Information | Backend Server | Suppliers | Tampering | 3 - Possible / Occasional | 3 | 4 - Severe | 4 | 12 | Medium | Low | Treat | 1. Supplier assurance, e.g., security management plan. - Principle 8 of NCSC Cloud Security Principles (Supply chain security) 2. Network access control to restrict access. - Principle 11 of NCSC Cloud Security Principles (External interface protection) Principle 12 of Cloud Security Principles (Secure service administration) 3. Monitoring for suspicious activity - Principle 5.2 of NCSC Cloud Security Principles (Protective monitoring) 4. Privileged user management - Principle 6.2 of NCSC Cloud Security Principles (Technical controls for service administration) | 3 - Possible / Occasional | 3 | 3 - Moderate | 3 | 9 | Medium
Risk 009 | There is a risk that the VPN could be overwhelmed preventing legitimate access to authorised users | Grant Management Service | Department of Artificial Intelligence and Robotic Technologies |  | SRO | IAO | Low | Risk was raised with SRO on 31/01/2023 and need to reduced to low | 31/01/2023 |  | No | VPN | VPN | Hardware malfunction or failure | Denial of Service | 3 - Possible / Occasional | 3 | 3 - Moderate | 3 | 9 | Medium | Low | Treat |  | 2 - Unlikely / Remote | 2 | 3 - Moderate | 3 | 6 | Low
Risk 010 | There is a risk that an employee with elevated privileges might make an accidental or unauthorised changed to the system resulting in a loss of integrity. | Grant Management Service | Department of Artificial Intelligence and Robotic Technologies |  | SRO | IAO | Low | Risk was raised with SRO on 31/01/2023 and risk will be accepted after successful treatment and reduction to Low. | 2023-05-04 |  | No | Grant Management Application (SaaS) | Application Server | Employee (privileged) | Tampering | 3 - Possible / Occasional | 3 | 3 - Moderate | 3 | 9 | Medium | Low | Treat | 1. Just-in-time privileged user management Principle 9 of NCSC Cloud Security Principles (Secure user management) 2. Proactive monitoring of privileged user activity Principle 5.2 of NCSC Cloud Security Principles (Protective monitoring) 3. Robust incident management procedure Principle 5.3 of NCSC Cloud Security Principles (Incident management) 4. Configuration and change manangement Principle 5.4 of NCSC Cloud Security Principles (Configuration and change management) | 2 - Unlikely / Remote | 2 | 2 - Marginal | 2 | 4 | Low
Risk 011 | There is a risk that a disgruntled employee with access to the grant management system, such as an employee or contractor might misuse their privilege and steal sensitive data, or amend company information resulting in fraudulent activity. | Grant Management Service | Department of Artificial Intelligence and Robotic Technologies |  | SRO | IAO | Low | Risk was raised with SRO on 31/01/2023 and risk will be accepted. | 2023-05-02 |  | No | Grant Management Application Database | Grant Management Application Database | Employee (disgruntled, coerced) | Information Disclosure | 2 - Unlikely / Remote | 2 | 3 - Moderate | 3 | 6 | Low | Low | Accept | Existing controls are sufficient to mitigate this risk. | 2 - Unlikely / Remote | 2 | 3 - Moderate | 3 | 6 | Low
Risk 012 | There is a risk that cyber criminals are able to cover their track by removing footprints from an activity resulting in repudiation of an activity. | Grant Management Service | Department of Artificial Intelligence and Robotic Technologies |  | SRO | IAO | Low | Risk was raised with SRO on 31/01/2023 and risk will be accepted after successful treatment and reduction to Low. | 2023-01-02 |  | No | Log Files | Backend Server | Cyber criminals | Repudiation | 3 - Possible / Occasional | 3 | 3 - Moderate | 3 | 9 | Medium | Low | Treat | 1. Log protection Principle 2.3 of Cloud Security Principles (Data encryption) Principle 5.2 of Cloud Security Principles (Protective monitoring) 2. Security monitoring Principle 5.2 of Cloud Security Principles (Protective monitoring) | 2 - Unlikely / Remote | 2 | 3 - Moderate | 3 | 6 | Low
Risk 013 | There is a risk that hostile state actors or cyber criminals might compromise a supplier's system by performing a supply chain attack, and use it gain unauthorised access to the grant management system resulting in loss of confidentiality and integrity. | Grant Management Service | Department of Artificial Intelligence and Robotic Technologies |  | SRO | IAO | Low | Risk was raised with SRO on 31/01/2023 and risk will be accepted after successful treatment and reduction to Low. | 2023-05-02 |  | No | Customer PII Customer Application Information | Backend Server | Hostile state actors | Information Disclosure | 3 - Possible / Occasional | 3 | 3 - Moderate | 3 | 9 | Medium | Low | Treat | 1. Supplier assurance, e.g., security management plan. - Principle 8 of NCSC Cloud Security Principles (Supply chain security) | 2 - Unlikely / Remote | 2 | 3 - Moderate | 3 | 6 | Low
Risk 014 | There is a risk that a hardware failure or malfunction might lead to the grant application system being unavailable to grant users resulting in system compromise and loss of availability. | Grant Management Service | Department of Artificial Intelligence and Robotic Technologies |  | SRO | IAO | Medium | Risk was raised with SRO on 31/01/2023 and need to reduced to low | 2023-05-02 |  | Yes | All Assets | All Components | Hardware malfunction or failure | Denial of Service | 3 - Possible / Occasional | 3 | 4 - Severe | 4 | 12 | Medium | Low | Treat | 1. SLA requirements based on risk Principle 2.5 of NCSC Cloud Security Principles (Physical resilience and availability) | 2 - Unlikely / Remote | 2 | 4 - Severe | 4 | 8 | Medium