## Introduction
This document is an example based on the ficticious Department of Artificial Intelligence and Robotic Technologies (DAIRT) corporation. The purpose of this document is to provide an example of how security controls can be documented, to support implementation and management of the controls. It is an example of an output from the activity “Implementing and assessing the effectiveness of security controls”. Security controls should be commensurate with information security risk, hence the risks should inform the types of controls that are implemented and the level/degree at which they are implemented. A defense in depth strategy should be used to mitigate risks. A single layer of security might be prone to attacks, employing a layered approach will improve the overall security posture of the service. Each layer of defense will serve as an additional barrier for potential attackers, making it difficult to gain unauthorised access or cause harm.

## Security Controls Implementatio
Principle 10 - Identity and Authentication Security Controls Implementation :
Control (Column AA in the Risk Treatment Plan) | Description | Implementation Status (Not Started, In Progress, Completed) | Responsible Team | Target Completion Date | Endpoint/Device | Product
User Provisioning | Automate user provisioning and deprovisioning processes | Not Started | Infrastructure Team | 2023-07-31 |  | UserProvisioner Software
Password Policy | Define and enforce strong password policies | In Progesss | Infrastructure Team | 2023-06-30 |  | SecurePass Password Policy
Single Sign-On (SSO) | Implement SSO for streamlined and secure user authentication | Not Started | Infrastructure Team | 2023-07-31 |  | UniSign SSO Solution
Identity and Access Management | Implement IAM solutions for centralised identity management | Not Started | Infrastructure Team | 2023-07-31 |  | IDAccess Manager Software
Biometric Authentication | Implement biometric-based authentication mechanisms | Not Started | Infrastructure Team | 2023-07-31 |  | BioAuthenticator Device
User Account Management | Develop processes for effective user account management | In Progesss | Infrastructure Team | 2023-06-30 |  | AccountManager System
Identity Verification | Establish identity verification procedures for user registration | Completed | Infrastructure Team | 2023-07-31 |  | VerifyID Verification System
Principle 9 - Secure User Management Security Controls Implementation :
Control | Description | Implementation Status | Responsible Team | Target Completion Date | Endpoint/Device | Product
User Provisioning | Automate user provisioning and deprovisioning processes | In Progesss | Infrastructure Team | 2023-07-31 |  | UserProvisioner Software | In Progress
User Access Reviews | Conduct periodic reviews of user access rights | Not Started | Infrastructure Team | 2023-08-31 |  | AccessReview+ Software | Not Started
Account Lockout Policy | Enforce temporary account lockouts after failed login attempts | In Progesss | Infrastructure Team | 2023-06-30 |  | LockoutShield Software | In Progress
User Activity Monitoring | Monitor user activity for suspicious behavior | Completed | Infrastructure Team | 2023-06-30 |  | ActivityGuard Software | In Progress
User Account Privilege Management | Control and manage user account privileges | Not Started | Infrastructure Team | 2023-07-31 |  | PrivilegeManager Software | Not Started
User Account Termination | Properly deactivate and remove user accounts | Not Started | Infrastructure Team | 2023-08-31 |  | AccountTerminator Software | Not Started
Principle 5.2 - Protective Monitoring Security Controls Implementation :
Control | Description | Implementation Status | Responsible Team | Target Completion Date | Endpoint/Device | Product
Log Collection and Storage | Collect and store logs for security monitoring | In Progress | Infrastructure Team | 2023-06-30 |  | LogCollector System
Log Analysis and Alerting | Analyse logs and generate alerts for suspicious activities | In Progress | Infrastructure Team | 2023-06-30 |  | AlertAnalyzer Software
Incident Response Planning | Develop a plan to effectively respond to security incidents | Not Started | Infrastructure Team | 2023-07-31 |  | IncidentResponse Planner Software
Incident Detection and Investigation | Detect and investigate security incidents in real-time | Not Started | Infrastructure Team | 2023-07-31 |  | IntrusionDetector System
Security Information and Event Management (SIEM) | Implement SIEM for centralised security event monitoring | Not Started | Infrastructure Team | 2023-07-31 |  | SIEM Software
Threat Intelligence Integration | Incorporate threat intelligence feeds into monitoring | Not Started | Infrastructure Team | 2023-08-31 |  | ThreatIntegrator System
Principle 2.3 - Data Encryption Security Controls Implementation :
Control | Description | Implementation Status | Responsible Team | Target Completion Date | Endpoint/Device | Product
Data Classification | Classify data based on sensitivity levels | In Progress | Infrastructure Team | 2023-06-30 |  | ClassificationTool Software
Encryption Policy | Define and implement encryption policies | Not Started | Infrastructure Team | 2023-07-31 |  | EncryptionPolicyManager Software
Data Encryption at Rest | Encrypt data while stored in databases and file systems | Not Started | Infrastructure Team | 2023-08-31 |  | DataEncryptor Software
Data Encryption in Transit | Encrypt data during transmission over networks | Not Started | Infrastructure Team | 2023-08-31 |  | SecureTransporter Software
Key Management | Establish procedures for secure key generation and storage | Not Started | Infrastructure Team | 2023-08-31 |  | KeyManager Software
Database Encryption | Implement encryption for sensitive data in databases | Not Started | Infrastructure Team | 2023-07-31 |  | DatabaseEncryptor Software
Principle 5.1 - Vulnerability Management Security Controls Implementation :
Control | Description | Implementation Status | Responsible Team | Target Completion Date | Endpoint/Device | Product
Asset Inventory | Maintain an inventory of all hardware and software assets | In Progress | Infrastructure Team | 2023-06-30 |  | AssetTracker Software
Vulnerability Scanning | Regularly scan systems and applications for vulnerabilities | In Progress | Infrastructure Team | 2023-07-15 |  | ScannerTool Software
Patch Management | Regularly apply security patches and updates | In Progress | Infrastructure Team | Ongoing |  | PatchGuard System
Vulnerability Remediation | Prioritise and remediate identified vulnerabilities | Not Started | Infrastructure Team | 2023-07-31 |  | RemediationManager Software
Configuration Management | Establish and enforce secure configuration baselines | Not Started | Infrastructure Team | 2023-07-31 |  | ConfigGuard System
Vulnerability Reporting and Metrics | Generate reports and metrics on vulnerability management | Not Started | Infrastructure Team | 2023-08-31 |  | ReportingTool Software
Principle 7 - Secure Development Security Controls Implementation :
Control | Description | Implementation Status | Responsible Team | Target Completion Date | Endpoint/Device | Product
Secure Coding Guidelines | Establish coding standards and guidelines for secure development | In Progress | Development Team | 2023-06-30 |  | CodingGuidelines Document
Code Review | Conduct code reviews to identify and remediate security issues | In Progress | Development Team | 2023-07-15 |  | CodeReviewer Software
Security Testing | Perform security testing to identify vulnerabilities and flaws | Not Started | Development Team | 2023-07-31 |  | SecurityTester Software
Security Training for Developers | Provide security training to developers on secure coding | Not Started | Development Team | 2023-08-31 |  | TrainingPlatform Software
Secure Development Lifecycle (SDL) | Implement a secure development lifecycle process | Not Started | Development Team | 2023-08-31 |  | SDLTool Software
Third-Team Library Management | Manage and update third-Team libraries and dependencies | In Progress | Development Team | 2023-06-30 |  | LibManager Software
Principle 2.5. - Physical Resilience and Availability Security Controls Implementation :
Control | Description | Implementation Status | Responsible Team | Target Completion Date | Endpoint/Device | Product
Business Impact Analysis | Assess the potential impact of disruptions on business operations | Not Started | Infrastructure Team | 2023-07-31 |  | ImpactAnalyzer Software
Redundancy and Failover | Implement redundancy and failover mechanisms for critical systems | In Progress | Infrastructure Team | 2023-07-15 |  | FailoverController Software
Disaster Recovery Plan | Develop and document a disaster recovery plan | Not Started | Infrastructure Team | 2023-08-31 |  | RecoveryPlanner Software
Backup and Restore | Implement regular data backup and restore procedures | In Progress | Infrastructure Team | Ongoing |  | BackupManager System
High Availability Architecture | Design and deploy high availability architecture | Not Started | Infrastructure Team | 2023-08-31 |  | AvailabilityArchitect Software
Incident Response Planning | Develop a plan to effectively respond to security incidents | Not Started | Infrastructure Team | 2023-07-31 |  | IncidentResponse Planner Software
Load Balancing | Implement load balancing for distributing network traffic | Not Started | Infrastructure Team | 2023-07-31 |  | LoadBalancer Hardware
Endpoint Detection and Response | Malware protection implemented on all devices and endpoints | Not Started | Infrastructure Team | 2023-07-31
Principle 11 - External Interface Protection Security Controls Implementation :
Control | Description | Implementation Status | Responsible Team | Target Completion Date | Endpoint/Device | Product
Network Perimeter Security | Implement security measures to protect external network perimeter | In Progress | Network Security Team | 2023-07-15 |  | PerimeterFirewall Device
Web Application Firewall (WAF) | Deploy a WAF to protect web applications from attacks | Not Started | Network Security Team | 2023-08-31 |  | WebAppFirewall Device
Intrusion Prevention System (IPS) | Implement an IPS to detect and block external intrusions | In Progress | Network Security Team | 2023-07-31 |  | IPSDevice
DDoS Mitigation | Deploy DDoS mitigation solutions to protect against attacks | Not Started | Network Security Team | 2023-08-31 |  | DDoSMitigator Device
Secure VPN Communication | Encrypt and secure VPN communication channels | In Progress | Network Security Team | 2023-06-30 |  | VPNGateway Device
Secure Remote Access | Implement secure mechanisms for remote access | In Progress | Network Security Team | 2023-06-30 |  | RemoteAccessGateway Device
Principle 8 - Supply Chain Security Controls Implementation :
Control | Description | Implementation Status | Responsible Team | Target Completion Date | Endpoint/Device | Product
Vendor Risk Assessment | Assess and evaluate the security risks of third-Team vendors | In Progress | Security Team | 2023-07-31 |  | RiskAssessmentTool Software
Supplier Security Requirements | Define security requirements for suppliers and vendors | Not Started | Procurement Team | 2023-07-31 |  | SupplierSecurityPolicy Document
Supplier Security Audits | Conduct security audits of suppliers and vendors | Not Started | Security Team | 2023-08-31 |  | AuditTool Software
Secure Software Development Lifecycle | Implement secure development practices in the software supply chain | In Progress | Development Team | 2023-06-30 |  | SecureDevLifecycle Process
Secure Code Review | Perform code reviews of third-party software for security issues | Not Started | Development Team | 2023-07-31 |  | CodeReviewer Software
Supplier Incident Response Planning | Collaborate with suppliers to establish incident response plans | Not Started | Security Team | 2023-08-31 |  | IncidentResponsePlanner Software
Principle 5.3 - Incident Management Security Controls Implementation :
Control | Description | Implementation Status | Responsible Team | Target Completion Date | Endpoint/Device | Product
Incident Response Plan | Develop a plan to effectively respond to security incidents | In Progress | Infrastructure Team | 2023-06-30 |  | ResponsePlan Document
Incident Detection and Monitoring | Implement tools and processes for detecting and monitoring incidents | In Progress | Infrastructure Team | 2023-07-15 |  | DetectionSystem Software
Incident Reporting and Escalation | Establish procedures for reporting and escalating security incidents | Not Started | Infrastructure Team | 2023-07-31 |  | ReportingTool Software
Incident Response Team | Form a dedicated team responsible for incident response | Not Started | Infrastructure Team | 2023-07-31 |  | IncidentResponseTeam Members
Forensic Investigation | Perform forensic investigation to identify the root cause of incidents | Not Started | Infrastructure Team | 2023-08-31 |  | ForensicTool Software
Lessons Learned and Improvements | Capture lessons learned from incidents and implement improvements | Not Started | Infrastructure Team | 2023-08-31 |  | LessonsLearned Database
Principle 5.4 - Configuration and Change Management Security Controls Implementation :
Control | Description | Implementation Status | Responsible Team | Target Completion Date | Endpoint/Device | Product
Configuration Baseline | Establish and maintain a secure configuration baseline | In Progress | Infrastructure Team | 2023-06-30 |  | ConfigBaseline Document
Change Management Process | Implement a process for reviewing and approving changes | In Progress | Infrastructure Team | 2023-06-30 |  | ChangeManagement Software
Change Request Management | Establish procedures for submitting and managing change requests | Not Started | Infrastructure Team | 2023-07-31 |  | ChangeRequest System
Configuration Item (CI) Management | Maintain an inventory of configuration items and their attributes | Not Started | Infrastructure Team | 2023-07-31 |  | CIManagement System
Configuration Auditing | Perform regular audits to ensure configuration compliance | Not Started | Infrastructure Team | 2023-08-31 |  | ConfigurationAuditor Software
Configuration Documentation | Document configuration details, including settings and dependencies | In Progress | Infrastructure Team | 2023-06-30 |  | ConfigDocumentation System
Access Control Security Controls Implementation:
Control | Description | Implementation Status | Responsible Team | Target Completion Date | Endpoint/Device | Product
User Authentication | User's identity is verified via a 2nd form of authentication before access is granted. Multi-factor authentication is implemented. | In Progress | Infrastructure Team | 2023-06-30 | Active Directory | SecureAuth System
Role-Based Access Control | Access rights are granted based on user roles | Not Started | Infrastructure Team | 2023-07-31 | Grant Management System | AccessControl+ Software
Access Control Policies | Defined policies for granting and revoking access | In Progress | Infrastructure Team | 2023-07-15 | Department policies | PolicyGuard Software
Access Logging | User access events are logged for audit and monitoring | In Progress | Infrastructure Team | 2023-06-30 | - Grant Management Saas Application - Grant Management Database | AuditTrail System
Privileged Access Management | Just in time access control is implemented on privileged user accounts. Privileged user access is monitored and reviewed. | Not Started | Infrastructure Team | 2023-07-31 | Active Directory | PrivAccess Control Software
Account Lockout Policy | User accounts are account locked out after 5 failed login attempts | In Progress | Infrastructure Team | 2023-06-30 | Active Directory | LockoutShield Software
Access Review | Process in place to regularly review and revoke unnecessary access | Not Started | Infrastructure Team | 2023-08-31 | - Grant Management Saas Application - Grant Management Database | AccessReview+ Software
Network Security Controls Implementation:
Control | Description | Implementation Status | Responsible Team | Target Completion Date | Endpoint/Device | Product
Firewalls | Deploy firewalls to monitor and filter network traffic | In Progress | Network Security Team | 2023-06-30 | Organisation network | ShieldDefender Firewall
Intrusion Detection System (IDS) | Implement an IDS to detect network intrusions | In Progress | Network Security Team | 2023-06-30 | Organisation network | IntruDetect Pro Software
Intrusion Prevention System (IPS) | Implement an IPS to prevent network intrusions | Not Started | Network Security Team | 2023-07-31 | Organisation network | IntruPrevent Pro Software
Network Segmentation | Divide the network into segments for improved security | Not Started | Network Security Team | 2023-07-31 | Organisation network | SecureSegment Hardware
VLANs | Implement Virtual Local Area Networks (VLANs) | Not Started | Network Security Team | 2023-07-31 | Organisation network | VirtuNet Network Devices
Network Access Control (NAC) | Implement NAC to control and authenticate network devices | Not Started | Network Security Team | 2023-07-31 | Organisation network | NetGuard NAC System
Network Monitoring | Implement network monitoring tools for threat detection | In Progress | Network Security Team | 2023-06-30 | Organisation network | SentinelMonitor Software
Patch Management | Regularly apply security patches and updates | In Progress | Infrastructure Team | Ongoing | Organisation network | PatchGuard System